## Backlog
|  |  | Unit price for man-month | 35000000 | 107.5 | mandays | 3.5833 | man-month | 125416666.6667 | VNĐ | 2.2333 | 78166666.6667
# | Task name |  | Note | State | Mandays | Start date | End date | Remark | Jira
A | System |  |  |  | 9
| F1 | Login/ Change Password | Feature |  | 2
| F2 | Role management | Feature |  | 3
| F3 | Permission management | Feature |  | 1
| F4 | User management | Feature |  | 3
B | Data visualization |  |  |  | 40.5
| F5 | Data Type Management | Feature |  | 3
| F6 | Data management | Feature |  | 5
| F7 | Data report | Feature |  | 2.5
| F8 | Create template (Pie Chart, Bar Chart, Line Chart, Area Chart, Combo Chart) | Feature (5 chart type) |  | 17
| F9 | Report views by the chart | Feature (5 chart type) |  | 13
C | Portfolio Management |  |  |  | 58
| F10 | Portfolio | Feature |  | 4
| F11 | Asset | Feature |  | 4
| F12 | Asset’s Market Price | Feature |  | 3
| F13 | Tax and fee | Feature |  | 3
| F14 | Transaction (buy/sell Asset) | Feature |  | 4.5
| F15 | Investor (buy/sell Portfolio) | Feature |  | 4.5
| F16 | Cash Management | Feature |  | 4.5
| F17 | Cert Balance | task schedure |  | 6
| F18 | Cash Balance | task schedure |  | 6
| F19 | Portfolio Balance | task schedure |  | 6
| F20 | EOD Net Asset Value | task schedure |  | 4
| F21 | Portfolio Report | Feature (chart) |  | 3.5
| F22 | NAV Report | Feature (chart) |  | 3.5
| F23 | Investor Report | Feature |  | 1.5
1 | Development | 125000000
2 | Domain
3 | Hosting
4 | SSL

## F1
Back | Login/ Change Password | Total | 2 | Mandays
ID | Task | Description | Mandays | Type | Responsible | Start date | End date | Remark
1 | Login |  | 0.5
2 | Forgot password |  | 0.5
3 | Change password |  | 0.5
4 | Sending a re-verification email |  | 0.5

## F2
Back | Role management | Total | 3 | Mandays
ID | Task | Description | Mandays | Type | Responsible | Start date | End date | Remark
1 | List roles - Export excel |  | 1
2 | Add new role |  | 1
3 | Edit role |  | 0.5
4 | Delete role |  | 0.5

## F3
Back | Permission management |  | 1 | Mandays
ID | Task | Description | Mandays | Type | Responsible | Start date | End date | Remark
1 | List permissions |  | 0.5
2 | Export Excel |  | 0.5

## F4
Back | User management |  | 3 | Mandays
ID | Task | Description | Mandays | Type | Responsible | Start date | End date | Remark
1 | List users |  | 0.5
2 | Add new user |  | 1
3 | Edit user |  | 1
4 | Export excel |  | 0.5

## F5
Back | Data Type Management |  | 3
ID | Task | Description | Mandays | Start date | End date | Remark
1 | List data type |  | 1
2 | Add new data type |  | 1
3 | Edit data type |  | 0.5
4 | Export excel |  | 0.5

## F6
Back | Data management |  | 5
ID | Task | Description | Mandays | Start date | End date | Remark
1 | List data |  | 1
2 | Add new data |  | 1
3 | Import data |  | 1
4 | Edit data |  | 1
5 | List and approve |  | 0.5
6 | Export excel |  | 0.5

## F7
Back | Data report |  | 2.5
ID | Task | Description | Mandays | Start date | End date | Remark
1 | List data |  | 2
6 | Export excel |  | 0.5

## F8
Back | Create template - Pie Chart, Bar Chart, Line Chart, Area Chart, Combo Chart |  | 17
ID | Task | Description | Mandays | Start date | End date | Remark
1 | List tempates |  | 1
2 | Init data |  | 1
3 | Pie Chart (Create/Edit/View example) |  | 3
4 | Bar Chart ((Create/Edit/View example) |  | 3
5 | Line Chart (Create/Edit/View example) |  | 3
6 | Area Chart (Create/Edit/View example) |  | 3
7 | Combo Chart (Create/Edit/View example) |  | 3

## F9
Back | Report views by the chart |  | 13
ID | Task | Description | Mandays | Start date | End date | Remark
1 | Init data |  | 1
2 | Pie Chart |  | 2
3 | Bar Chart |  | 2
4 | Line Chart |  | 2
5 | Area Chart |  | 2
6 | Combo Chart |  | 2
7 | Export excel |  | 1
8 | Chart save PDF |  | 1

## F10
Back | Portfolio |  | 4
ID | Task | Description | Mandays | Start date | End date | Remark
1 | List portfolio |  | 1
2 | Add new portfolio |  | 1
3 | Edit portfolio |  | 1
4 | List and approve |  | 0.5
5 | Export excel |  | 0.5

## F11
Back | Asset |  | 4
ID | Task | Description | Mandays | Start date | End date | Remark
1 | List assets |  | 1
2 | Add new asset |  | 1
3 | Edit asset |  | 1
4 | List and approve |  | 0.5
5 | Export excel |  | 0.5

## F12
Back | Asset’s Market Price |  | 3
ID | Task | Description | Mandays | Start date | End date | Remark
1 | List Asset’s Market Price |  | 0.5
2 | Add Asset’s Market Price |  | 1
3 | Edit Asset’s Market Price |  | 0.5
4 | List and approve |  | 0.5
5 | Export excel |  | 0.5

## F13
Back | Tax and fee |  | 3
ID | Task | Description | Mandays | Start date | End date | Remark
1 | List tax & fee |  | 0.5
2 | Add tax & fee |  | 1
3 | Edit tax & fee |  | 0.5
4 | List and approve |  | 0.5
5 | Export excel |  | 0.5

## F14
Back | Transaction (buy/sell Asset) |  | 4.5
ID | Task | Description | Mandays | Start date | End date | Remark
1 | List transaction |  | 1
2 | Add transaction |  | 1
3 | Edit transaction |  | 1
4 | List and approve |  | 1
5 | Export excel |  | 0.5

## F15
Back | Investor (buy/sell Portfolio) |  | 4.5
ID | Task | Description | Mandays | Start date | End date | Remark
1 | List Investors |  | 1
2 | Add Investor |  | 1
3 | Edit Investor |  | 1
4 | List and approve |  | 1
5 | Export excel |  | 0.5

## F16
Back | Cash Management |  | 4.5
ID | Task | Description | Mandays | Start date | End date | Remark
1 | List cash transaction |  | 1
2 | Add cash transaction |  | 1
3 | Edit cash transaction |  | 1
4 | List and approve |  | 1
5 | Export excel |  | 0.5

## F17
Back | Cert Balance |  | 6
ID | Task | Description | Mandays | Start date | End date | Remark
1 | Job run dailly |  | 3
2 | Job run real time |  | 3

## F18
Back | Cash Balance |  | 6
ID | Task | Description | Mandays | Start date | End date | Remark
1 | Job run dailly |  | 2
2 | Job run real time |  | 4

## F19
Back | Portfolio Balance |  | 6
ID | Task | Description | Mandays | Start date | End date | Remark
1 | Job run dailly |  | 2
2 | Job run real time |  | 4

## F20
Back | EOD Net Asset Value |  | 4
ID | Task | Description | Mandays | Start date | End date | Remark
1 | Job run dailly |  | 4

## F21
Back | Portfolio Report |  | 3.5
ID | Task | Description | Mandays | Start date | End date | Remark
1 | Init data |  | 0.5
2 | Report view |  | 1
3 | Chart view |  | 2

## F22
Back | NAV Report |  | 3.5
ID | Task | Description | Mandays | Start date | End date | Remark
1 | Init data |  | 0.5
2 | Report view |  | 1
3 | Chart view |  | 2

## F23
Back | Investor Report |  | 1.5
ID | Task | Description | Mandays | Start date | End date | Remark
1 | Init data |  | 0.5
2 | Report view |  | 1